## ULTRASAT Gantt
Task Name | Duration | Start | Finish | Predecessors | Assigned To | % Complete | Status | Comments
Project Management (1.1) | 1067d | 2020-12-01 | 2025-01-01 |  |  | 4%
System Engineering | 153d | 2020-12-01 | 2021-07-01 |  |  | 59%
General design (Puzzle documents) | 65d | 2020-12-01 | 2021-03-01 |  | Puzzle | 100% | Complete
Project timeline planning | 46d | 2021-05-01 | 2021-07-01 |  | Lior
Integrated Logistic Support (ILS) = Project Maintenance Plan | 696d | 2021-04-01 | 2023-11-30
Collect information | 261d | 2021-04-01 | 2022-03-31 |  | Lior
Design | 262d | 2021-06-01 | 2022-06-01 |  | Lior
Write documents and procedures | 262d | 2022-06-02 | 2023-06-04 | 8 | Lior
Write documentation for system parts | 131d | 2023-06-01 | 2023-11-30
SOC Standard Operating Procedure (SOP) & Training | 566d | 2021-05-01 | 2023-06-29
Collect information | 262d | 2021-05-01 | 2022-05-01 |  | Lior
Design | 44d | 2022-05-01 | 2022-06-29 |  | Lior
Write SOC operating procedures | 261d | 2022-07-01 | 2023-06-29 |  | Lior
Write SOC training materials | 261d | 2022-07-01 | 2023-06-29 |  | Lior
Architectural Design | 101d | 2021-05-01 | 2021-09-16
Current Building | 35d | 2021-05-01 | 2021-06-16
Comm | 35d | 2021-05-01 | 2021-06-16
SOC | 35d | 2021-05-01 | 2021-06-16
Offices | 35d | 2021-05-01 | 2021-06-16
New Building | 101d | 2021-05-01 | 2021-09-16
Comm | 101d | 2021-05-01 | 2021-09-16
SOC | 101d | 2021-05-01 | 2021-09-16
Offices | 101d | 2021-05-01 | 2021-09-16
Hardware Procurement | 960d | 2021-05-01 | 2025-01-01 |  | Lior
Comm (Servers, Storage, Network) Room | 566d | 2021-05-01 | 2023-06-29 |  | Lior
Specifications | 22d | 2023-01-01 | 2023-01-30 |  | Lior
Servers - Primary & Backup | 87d | 2023-01-01 | 2023-05-01 |  | Lior
Storage - Primary & Backup | 130d | 2023-01-01 | 2023-06-29 |  | Lior
Racks, Switches, Etc. | 130d | 2023-01-01 | 2023-06-29
Comm, Elect, A/C (Check with Hemda) | 67d | 2021-05-01 | 2021-08-01 |  | Lior
SOC | 132d | 2023-01-01 | 2023-07-03 |  | Lior
Specifications | 22d | 2023-01-01 | 2023-01-30
Workstations | 132d | 2023-01-01 | 2023-07-03
Monitors (Wall + Desktop) | 132d | 2023-01-01 | 2023-07-03
Office | 110d | 2023-01-01 | 2023-06-01 |  | Lior
Specifications | 1d | 2023-01-01 | 2023-01-01
Workstations | 110d | 2023-01-01 | 2023-06-01
Monitors | 110d | 2023-01-01 | 2023-06-01
New Building and Auditorium | 263d | 2024-01-01 | 2025-01-01
Specifications | 44d | 2024-01-01 | 2024-02-29
Procurement - Comm, SOC, Office | 220d | 2024-03-01 | 2025-01-01
Misc | 198d | 2023-04-01 | 2024-01-01 |  | Lior
Procurement of spare parts | 1d | 2024-01-01 | 2024-01-01
Track procurement and manage installation | 1d | 2023-04-01 | 2023-04-01
Infrastructure (1.2) | 1131d | 2021-01-01 | 2025-05-01
Comm (Servers, Storage, Network) Room - Primary & Backup | 676d | 2021-05-01 | 2023-11-30 |  | Lior
Passive (Cables, Connectors) | 67d | 2021-05-01 | 2021-08-01
Active (Racks, Network switches, network connection) | 65d | 2023-01-01 | 2023-03-30
Installation and Setup | 131d | 2023-06-01 | 2023-11-30
Servers installation & configuration | 88d | 2023-06-01 | 2023-10-02
Storage installation & configuration | 88d | 2023-08-01 | 2023-11-30
Network setup | 88d | 2023-08-01 | 2023-11-30
Server, Storage, Network - Evaluation | 66d | 2023-09-01 | 2023-11-30
SOC Room | 481d | 2021-05-01 | 2023-03-02
Passive (Cables, Connectors) | 67d | 2021-05-01 | 2021-08-01
Active (Racks, Network switches, network connection) | 45d | 2023-01-01 | 2023-03-02
Multimedia - Monitors, Matrix | 45d | 2023-01-01 | 2023-03-02
Visitor Center - New Building - TBD | 87d | 2025-01-01 | 2025-05-01
Passive (Racks, Cables, Connectors) | 87d | 2025-01-01 | 2025-05-01
Active (Network switches, network connection) | 87d | 2025-01-01 | 2025-05-01
Multimedia | 87d | 2025-01-01 | 2025-05-01
WIS Network Requirements | 566d | 2021-05-01 | 2023-06-29
Write detailed specifications for the hardware and networking components | 90d | 2021-05-01 | 2021-09-01
Network installation and setup | 500d | 2021-08-01 | 2023-06-29
Secured Interfaces to IAI (see also Cyber) | 326d | 2021-01-01 | 2022-03-31
Communication | 66d | 2022-01-01 | 2022-03-31 |  | Lior
Fiber / ADSL / Redundancy | 44d | 2022-01-01 | 2022-03-01 |  | Lior
IPSec / Cyber / Firewall / VPN | 44d | 2022-01-01 | 2022-03-01 |  | Lior
Integration & Testing | 23d | 2022-03-01 | 2022-03-31 |  | Lior
Protocol specifications with IAI - XML etc. | 284d | 2021-01-01 | 2022-02-01 |  | Yossi
Secured WEB Interfaces (see also Cyber) | 154d | 2022-01-01 | 2022-08-02
Specifications | 110d | 2022-01-01 | 2022-06-01 |  | Lior
Check cyber aspects | 110d | 2022-01-01 | 2022-06-01 |  | Lior
Procurement | 44d | 2022-06-02 | 2022-08-02 | 79 | Lior
Observation, Operation, Management, Control (1.3) [Software] | 371d | 2021-04-01 | 2022-09-01
Operations - SOC Command & Control | 305d | 2021-04-01 | 2022-06-01
Functional design | 196d | 2021-04-01 | 2021-12-30 |  | Chen
Software design | 196d | 2021-04-01 | 2021-12-30 |  | Chen
GUI design | 176d | 2021-05-01 | 2021-12-30 |  | Chen
Design Review | 1d | 2021-12-30 | 2021-12-30
Software development | 109d | 2022-01-01 | 2022-05-31 |  | Chen
QA & Testing | 67d | 2022-03-01 | 2022-06-01
Testing | 67d | 2022-03-01 | 2022-06-01 |  | QA
Fixes & Improvements | 67d | 2022-03-01 | 2022-06-01 |  | Chen
Delivery Review | 1d | 2022-06-01 | 2022-06-01
Observation Planning | 351d | 2021-05-01 | 2022-09-01
Functional design | 176d | 2021-05-01 | 2021-12-30 |  | Yossi
Software design | 87d | 2021-09-01 | 2021-12-30 |  | Chen
GUI design | 66d | 2021-09-01 | 2021-12-01 |  | Chen
Design Review | 1d | 2021-12-30 | 2021-12-30
Algorithms development | 66d | 2022-01-01 | 2022-03-31 |  | Eran
Software development | 66d | 2022-01-01 | 2022-03-31 |  | Chen
GUI development - Desktop / Web | 67d | 2022-05-01 | 2022-08-01 |  | Chen
QA & Testing | 67d | 2022-06-01 | 2022-09-01
Testing | 67d | 2022-06-01 | 2022-09-01 |  | QA
Fixes & Improvements | 67d | 2022-06-01 | 2022-09-01 |  | Chen
Delivery Review | 1d | 2022-06-01 | 2022-06-01
External Interfaces (1.4) - [Software] | 523d | 2021-12-30 | 2024-01-01
IAI Interface | 261d | 2021-12-30 | 2022-12-29
Complete protocol specifications with IAI-GCS | 22d | 2022-02-01 | 2022-03-02 |  | Yossi
Design Review | 1d | 2021-12-30 | 2021-12-30
Develop Incoming images handling - from IAI to Pipeline | 261d | 2022-01-01 | 2022-12-29 |  | Chen
Develop Metadata handling - from IAI to Pipeline and Managers | 261d | 2022-01-01 | 2022-12-29 |  | Chen
Develop Command & Control aspects | 261d | 2022-01-01 | 2022-12-29 |  | Chen
Develop Simulators and testing tools | 261d | 2022-01-01 | 2022-12-29 |  | Chen
QA & Testing | 218d | 2022-03-01 | 2022-12-29 |  | QA
Testing specifications | 1d | 2022-03-01 | 2022-03-01 |  | QA
Testing | 1d | 2022-04-01 | 2022-04-01 |  | QA
Fixes & Improvements | 196d | 2022-04-01 | 2022-12-29 |  | Chen
Delivery Review | 1d | 2022-06-01 | 2022-06-01
NASA Interface | 262d | 2022-06-01 | 2023-06-01
Communication - Infrastructure | 110d | 2022-08-01 | 2023-01-01 |  | Lior
Fiber / ADSL / Redundancy | 89d | 2022-08-01 | 2022-12-01 |  | Lior
IPSec / Cyber / Firewall | 89d | 2022-08-01 | 2022-12-01 |  | Lior
Integration & Testing | 22d | 2022-12-01 | 2023-01-01 |  | QA
Design - requirements, protocols, access | 153d | 2022-06-01 | 2023-01-01 |  | Yossi
Design Review | 1d | 2022-12-30 | 2022-12-30
Development | 110d | 2023-01-01 | 2023-06-01 |  | Chen
QA & Testing | 87d | 2023-02-01 | 2023-06-01 |  | QA
Write testing documents | 21d | 2023-02-01 | 2023-03-01
Testing | 67d | 2023-03-01 | 2023-06-01 |  | QA
Fixes & Improvements | 67d | 2023-03-01 | 2023-06-01 |  | Chen
Delivery Review | 1d | 2024-01-01 | 2024-01-01
DESY Interface | 217d | 2022-06-01 | 2023-03-30
Communication - Infrastructure | 109d | 2022-08-01 | 2022-12-29 |  | Lior
Fiber / ADSL / Redundancy | 89d | 2022-08-01 | 2022-12-01 |  | Lior
IPSec / Cyber / Firewall | 89d | 2022-08-01 | 2022-12-01 |  | Lior
Integration & Testing | 21d | 2022-12-01 | 2022-12-29 |  | QA
Design - requirements, protocols, access | 153d | 2022-06-01 | 2023-01-01 |  | Yossi
Design Review | 1d | 2022-12-30 | 2022-12-30
Development | 65d | 2023-01-01 | 2023-03-30 |  | Chen
QA & Testing | 44d | 2023-01-01 | 2023-03-01 |  | QA
Write testing documents | 24d | 2023-01-01 | 2023-02-01 |  | QA
Testing | 21d | 2023-02-01 | 2023-03-01 |  | QA
Fixes & Improvements | 21d | 2023-02-01 | 2023-03-01 |  | Chen
Delivery Review | 1d | 2024-01-01 | 2024-01-01
LSST Interface | 183d | 2022-08-01 | 2023-04-12
Communication - Infrastructure | 109d | 2022-08-01 | 2022-12-29 |  | Lior
Fiber / ADSL / Redundancy | 89d | 2022-08-01 | 2022-12-01 |  | Lior
IPSec / Cyber / Firewall | 89d | 2022-08-01 | 2022-12-01 |  | Lior
Integration & Testing | 21d | 2022-12-01 | 2022-12-29 |  | QA
Design - requirements, protocols, access | 2w |  |  |  | Yossi
Design Review | 1d | 2022-12-30 | 2022-12-30
Development | 4w | 2023-01-01 | 2023-01-26 |  | Chen
QA & Testing | 31d | 2023-03-01 | 2023-04-12 |  | QA
Write testing documents | 1w | 2023-03-01 | 2023-03-07 |  | Lior
Testing | 2w | 2023-04-01 | 2023-04-12 |  | QA
Fixes & Improvements | 2w | 2023-04-01 | 2023-04-12 |  | Chen
Delivery Review | 1d | 2024-01-01 | 2024-01-01
Image & Data Processing (1.5) [Software] | 521d | 2021-01-01 | 2022-12-30
Pipeline (MATLAB) | 521d | 2021-01-01 | 2022-12-30
Functional design | 240d | 2021-01-01 | 2021-12-01 |  | Eran |  | In Progress
Databases design | 240d | 2021-01-01 | 2021-12-01 |  | Eran |  | In Progress
AstroPack Packages/Class design | 198d | 2021-03-01 | 2021-12-01 |  | Eran |  | In Progress
Base classes (Header, Containers, etc) | 188d | 2021-03-15 | 2021-12-01 |  | Eran |  | In Progress
Base classes - Log, Database | 67d | 2021-03-01 | 2021-06-01 |  | Chen
Pipeline Manager | 67d | 2021-05-01 | 2021-08-01 |  | Chen
Phase 1: Single step process - From RawImage to Products |  |  |  |  | Eran
GUI Design
Design & Status Review | 1d | 2021-08-30 | 2021-08-30
Phase 2: LAST Project - Testcase
Specifications |  |  |  |  | Eran
Additional development |  |  |  |  | Eran
Additional development |  |  |  |  | Chen
QA & Testing |  |  |  |  | Sagi
Fixes & Improvements |  |  |  |  | Chen
LAST Delivery Review | 1d | 2022-12-30 | 2022-12-30
Develop Pipeline GUI | 2w |  |  |  | Chen
Pipeline Development
QA & Testing |  |  |  |  | QA
Write testing documents | 1w |  |  |  | QA
Testing | 8w |  |  |  | QA
Fixes | 4w |  |  |  | Eran
Source code documentation & help | 2w | 2021-12-01 | 2021-12-14 |  | Eran
WIS Databases & Archives | 1d | 2022-12-30 | 2022-12-30
Specifications and design | 1w |  |  |  | Yossi
Configurations - databases, replications, etc. | 2w |  |  |  | Chen
Design Review | 1d | 2022-12-30 | 2022-12-30
Development | 8w |  |  |  | Chen
QA & Testing |  |  |  |  | QA
Write testing documents | 1w |  |  |  | QA
Testing | 4w |  |  |  | QA
Fixes & Improvements | 4w |  |  |  | Chen
Data Archiving and Accessibility (1.6) [Software] | 263d | 2022-12-30 | 2024-01-01
Databases & Archives | 1d | 2022-12-30 | 2022-12-30
Requirements and design | 2w |  |  |  | Yossi
Design Review | 1d | 2022-12-30 | 2022-12-30
Development | 8w |  |  |  | Chen
QA & Testing
Write testing documents | 1w |  |  |  | QA
Testing | 4w |  |  |  | QA
Fixes & Improvements | 4w |  |  |  | Chen
Delivery Review | 1d | 2024-01-01 | 2024-01-01
Products Access | 1d | 2022-12-30 | 2022-12-30
Requirements and design | 2w |  |  |  | Yossi
Design Review | 1d | 2022-12-30 | 2022-12-30
Development (WebApp & MobileApp) | 16w |  |  |  | Chen
Additional tools design and development (Signal-to-Noise, etc.) | 16w |  |  |  | Chen
QA & Testing
Write testing documents and procedures | 1w |  |  |  | QA
Testing | 4w |  |  |  | QA
Fixed & Improvements | 4w |  |  |  | Chen
Delivery Review | 1d | 2024-01-01 | 2024-01-01
Alerts Access | 1d | 2022-12-30 | 2022-12-30
Requirements and design |  |  |  |  | Yossi
Design Review | 1d | 2022-12-30 | 2022-12-30
Development - Handle incoming alerts | 2w |  |  |  | Chen
Development - Outgoing alerts | 2w |  |  |  | Chen
Development (WebApp & MobileApp) | 4w |  |  |  | Chen
QA & Testing
Write testing documents and procedures | 1w |  |  |  | QA
Testing | 2w |  |  |  | QA
Fixed & Improvements | 2w |  |  |  | Chen
Delivery Review | 1d | 2024-01-01 | 2024-01-01
Partial Pipeline | 1d | 2022-12-30 | 2022-12-30
Requirements and design |  |  |  |  | Eran
Design Review | 1d | 2022-12-30 | 2022-12-30
Algorithms Development |  |  |  |  | Eran
Development |  |  |  |  | Chen
QA & Testing
Testing |  |  |  |  | QA
Fixed & Improvements |  |  |  |  | Eran
Fixed & Improvements |  |  |  |  | Chen
Delivery Review | 1d | 2024-01-01 | 2024-01-01
SOC System Management (1.7) [Software] | 1d | 2022-12-30 | 2022-12-30
SW & HW Infrastructure Architecture
Requirements and design |  |  |  |  | Team
Internal & External Interfaces [Development] - Remove - Duplicate with 1.4
IAI
Detailed protocol specifications
DESY
Detailed protocol specifications
NASA
Detailed protocol specifications
Public
Detailed protocol specifications
SOC HMI Concept (GUI) | 1d | 2022-12-30 | 2022-12-30
Design - Functional requirements | 1w |  |  |  | Chen
Design - UX | 2w |  |  |  | Chen
Design Review | 1d | 2022-12-30 | 2022-12-30
Evaluation and improvements | 1w |  |  |  | Team
Cyber - Requirements and Implementation (VPN in most cases)
IAI | 1w |  |  |  | Lior
DESY | 1w |  |  |  | Lior
NASA | 1w |  |  |  | Lior
LSST | 1w |  |  |  | Lior
Public | 1w |  |  |  | Lior
Procedures and Rule Engine [Development] | 1d | 2022-12-30 | 2022-12-30
Design Review | 1d | 2022-12-30 | 2022-12-30
Alerts | 1w |  |  |  | Chen
Target of Opportunity | 1w |  |  |  | Chen
Transients | 1w |  |  |  | Chen
Task Scheduler | 1w |  |  |  | Chen
Pending tasks | 1w |  |  |  | Chen
QA & Testing
Write testing documents and procedures | 1w |  |  |  | QA
Testing | 2w |  |  |  | QA
Fixed & Improvements | 2w |  |  |  | Chen
System Monitoring
Design Review | 1d | 2022-12-30 | 2022-12-30
QA & Testing
Write testing documents and procedures | 1w |  |  |  | QA
Testing | 2w |  |  |  | QA
Fixed & Improvements | 2w |  |  |  | Chen
Component Testing
QA & Testing
Write testing documents and procedures | 1w |  |  |  | QA
Testing | 2w |  |  |  | QA
Fixed & Improvements | 2w |  |  |  | Chen
QA & Integration + Acceptance Tests (1.9)
SOC Internal - Software Component
QA & Testing
Write testing documents and procedures | 2w |  |  |  | QA
Testing | 2w |  |  |  | QA
Fixed & Improvements | 2w |  |  |  | Chen
SOC Internal - SOC Components Integration (HW+SW)
QA & Testing
Write testing documents and procedures | 1w |  |  |  | QA
Testing | 2w |  |  |  | QA
Fixed & Improvements | 2w |  |  |  | Chen
SOC External - IAI
Write integration documents | 2w |  |  |  | QA
Design automation & manual testing |  |  |  |  | QA
Develop automation & simulations |  |  |  |  | QA
Run automation |  |  |  |  | QA
Perform manual testing |  |  |  |  | QA
Fixes and improvements
Acceptance tests
SOC External - DESY
Write integration documents | 2w |  |  |  | QA
Design automation & manual testing |  |  |  |  | QA
Develop automation & simulations |  |  |  |  | QA
Run automation |  |  |  |  | QA
Perform manual testing |  |  |  |  | QA
Fixes and improvements
Acceptance tests
SOC External - NASA
Write integration documents | 2w |  |  |  | QA
Design automation & manual testing |  |  |  |  | QA
Develop automation & simulations |  |  |  |  | QA
Run automation |  |  |  |  | QA
Perform manual testing |  |  |  |  | QA
Fixes and improvements
Acceptance tests
SOC External - LSST
Write integration documents | 2w |  |  |  | QA
Design automation & manual testing |  |  |  |  | QA
Develop automation & simulations |  |  |  |  | QA
Run automation |  |  |  |  | QA
Perform manual testing |  |  |  |  | QA
Fixes and improvements
Acceptance tests
Training and Documentation (1.10)
SOC Operation Simulator Development
Requirements and design
Write scenarios
Software design
Software development
Evaluation
QA & Testing
Write testing documents and procedures | 1w |  |  |  | QA
Testing | 2w |  |  |  | QA
Fixed & Improvements | 2w |  |  |  | Chen
Documentation
Write operating procedures
Write troubleshooting procedures
Write maintenance procedures
Training Materials
Write training docuements |  |  |  |  | TechWriter
Help Desk (originally in 1.3.3)
Requirements
Research available products (Check UVDesk) |  |  |  |  | Chen
Functional design
Write procedures
Develop plugins if required (Optional) |  |  |  |  | Chen
Write training materials
Evaluation