## ULTRASAT MASTER Gantt
Task Name | Duration | Start | Finish | Predecessors | Assigned To | % Complete | Status | Comments
ULTRASAT MASTER GANTT & MILESTONES
System Engineering & Infrastructure | 506d | 2021-12-27 | 2023-12-04
New Building - Infrastructure Preliminary Design Review | 4d | 2021-12-27 | 2021-12-30
Current Building - Infrastructure Critical Design Review | 3d | 2022-07-01 | 2022-07-04
Hardware Procurement | 196d | 2023-01-01 | 2023-10-01
Current Building - Infrastructure Readiness Review | 3d | 2023-12-01 | 2023-12-04
Software Development | 351d | 2022-03-01 | 2023-07-04
SOC - Pipeline, Operations, Observations, IAI Interface, DESY | 263d | 2022-03-01 | 2023-03-02
Critical Design Review | 3d | 2022-03-01 | 2022-03-03
Delivery Review | 2d | 2023-03-01 | 2023-03-02
Products Access, Help-Desk, NASA, LSST (WebApps, GUI, SQL, Python API, Mobile | 90d | 2023-03-01 | 2023-07-04
Critical Design Review | 3d | 2023-03-01 | 2023-03-05
Delivery Review | 4d | 2023-07-01 | 2023-07-04
Integration & Acceptance Tests | 242d | 2023-03-01 | 2024-02-01
SOC Internal Integration | 156d | 2023-07-01 | 2024-02-01
IAI Interface Integration | 176d | 2023-06-01 | 2024-02-01
Other Interfaces Integration - DESY, NASA, LSST | 67d | 2023-11-01 | 2024-02-01
Training Materials & Documentation (including Simulator Development) | 242d | 2023-03-01 | 2024-02-01
SOC System Readiness Review | 2d | 2024-02-01 | 2024-02-04
SOC Operators Trainning | 130d | 2024-02-04 | 2024-08-01
SOC Operational | 2d | 2024-08-01 | 2024-08-04