## ULTRASAT Gantt
Task Name | Duration | Start | Finish | Predecessors | Assigned To | % Complete | Status | Comments
ULTRASAT PROJECT GANTT
Last updated: 08/06/2021
Project Management (1.1) | 1068d | 2020-12-01 | 2025-01-02 |  |  | 3%
System Engineering | 153d | 2020-12-01 | 2021-07-01 |  |  | 42%
General design (Puzzle documents) | 65d | 2020-12-01 | 2021-03-01 |  | Puzzle | 100% | Complete
Project timeline planning | 88d | 2021-03-02 | 2021-07-01 | 7 | Lior
Integrated Logistic Support (ILS) = Project Maintenance Plan | 696d | 2021-04-01 | 2023-11-30
Collect information | 261d | 2021-04-01 | 2022-03-31 |  | Lior
Design | 262d | 2021-06-01 | 2022-06-01 |  | Lior
Write documents and procedures | 391d | 2022-06-02 | 2023-11-30 | 12 | Lior
Write documentation for system parts | 391d | 2022-06-02 | 2023-11-30 | 12 | Lior
SOC Standard Operating Procedure (SOP) & Training | 566d | 2021-05-01 | 2023-06-29
Collect information | 262d | 2021-05-01 | 2022-05-01 |  | Lior
Design | 44d | 2022-05-01 | 2022-06-29 |  | Lior
Write SOC operating procedures | 261d | 2022-06-30 | 2023-06-29 | 18 | Lior
Write SOC training materials | 261d | 2022-06-30 | 2023-06-29 | 18 | Lior
Architectural Design | 176d | 2021-05-01 | 2021-12-30
Current Building | 35d | 2021-05-01 | 2021-06-16
Comm | 35d | 2021-05-01 | 2021-06-16 |  | Lior
SOC | 35d | 2021-05-01 | 2021-06-16 |  | Lior
Offices | 35d | 2021-05-01 | 2021-06-16 |  | Lior
New Building | 176d | 2021-05-01 | 2021-12-30
Comm | 176d | 2021-05-01 | 2021-12-30 |  | Lior
SOC | 176d | 2021-05-01 | 2021-12-30 |  | Lior
Offices | 176d | 2021-05-01 | 2021-12-30 |  | Lior
Hardware Procurement | 961d | 2021-05-01 | 2025-01-02 |  | Lior
Comm (Servers, Storage, Network) Room | 588d | 2021-05-01 | 2023-07-31 |  | Lior
Specifications | 22d | 2023-01-01 | 2023-01-30 |  | Lior
Servers - Primary & Backup | 93d | 2023-01-31 | 2023-06-08 | 34 | Lior
Storage - Primary & Backup | 130d | 2023-01-31 | 2023-07-31 | 34 | Lior
Racks, Switches, Etc. | 130d | 2023-01-31 | 2023-07-31 | 34 | Lior
Comm, Elect, A/C (Check with Hemda) | 67d | 2021-05-01 | 2021-08-01 |  | Lior
SOC | 154d | 2023-01-01 | 2023-08-02 |  | Lior
Specifications | 22d | 2023-01-01 | 2023-01-30 |  | Lior
Workstations | 132d | 2023-01-31 | 2023-08-02 | 40 | Lior
Monitors (Wall + Desktop) | 132d | 2023-01-31 | 2023-08-02 | 40 | Lior
Office | 134d | 2023-01-01 | 2023-07-05
Specifications | 24d | 2023-01-01 | 2023-02-01 |  | Lior
Workstations | 110d | 2023-02-02 | 2023-07-05 | 44 | Lior
Monitors | 110d | 2023-02-02 | 2023-07-05 | 44 | Lior
New Building and Auditorium | 264d | 2024-01-01 | 2025-01-02
Specifications | 44d | 2024-01-01 | 2024-02-29 |  | Lior
Procurement - Comm, SOC, Office | 220d | 2024-03-03 | 2025-01-02 | 48 | Lior
Infrastructure (1.2) | 1131d | 2021-01-01 | 2025-05-01
Comm (Servers, Storage, Network) Room - Primary & Backup | 639d | 2021-05-01 | 2023-10-10
Passive (Cables, Connectors) | 67d | 2021-05-01 | 2021-08-01 |  | Lior
Active (Racks, Network switches, network connection) | 65d | 2023-01-01 | 2023-03-30 |  | Lior
Installation and Setup | 88d | 2023-06-11 | 2023-10-10 | 35
Servers installation & configuration | 88d | 2023-06-11 | 2023-10-10 |  | Lior
Storage installation & configuration | 88d | 2023-06-11 | 2023-10-10 |  | Lior
Network setup | 88d | 2023-06-11 | 2023-10-10 |  | Lior
Server, Storage, Network - Evaluation | 66d | 2023-06-11 | 2023-09-10 |  | Lior
SOC Room | 635d | 2021-05-01 | 2023-10-04
Passive (Cables, Connectors) | 67d | 2021-05-01 | 2021-08-01 |  | Lior
Active (Racks, Network switches, network connection) | 45d | 2023-08-03 | 2023-10-04 | 39 | Lior
Multimedia - Monitors, Matrix | 45d | 2023-08-03 | 2023-10-04 | 39 | Lior
Visitor Center - New Building - TBD | 87d | 2025-01-01 | 2025-05-01
Passive (Racks, Cables, Connectors) | 87d | 2025-01-01 | 2025-05-01 |  | Lior
Active (Network switches, network connection) | 87d | 2025-01-01 | 2025-05-01 |  | Lior
Multimedia | 87d | 2025-01-01 | 2025-05-01 |  | Lior
WIS Network Requirements | 590d | 2021-05-01 | 2023-08-02
Write detailed specifications for the hardware and networking components | 90d | 2021-05-01 | 2021-09-01 |  | Lior
Network installation and setup | 500d | 2021-09-02 | 2023-08-02 | 69 | Lior
Secured Interfaces to IAI (see also Cyber) | 498d | 2021-01-01 | 2022-11-28
Communication | 433d | 2021-04-01 | 2022-11-28 |  | Lior
Specifications | 110d | 2021-04-01 | 2021-09-01 |  | Lior
Fiber / ADSL / Redundancy | 21d | 2022-09-02 | 2022-09-29 |  | Lior
IPSec / Cyber / Firewall / VPN | 21d | 2022-10-02 | 2022-10-30 | 74 | Lior
Integration & Testing | 21d | 2022-10-31 | 2022-11-28 | 75 | Lior
Protocol specifications with IAI - XML etc. | 284d | 2021-01-01 | 2022-02-01 |  | Yossi
Protocol Review | 7d | 2022-02-02 | 2022-02-10 | 77
Secured WEB Interfaces (DESY, NASA, LSST, Public) - see also Cyber | 154d | 2023-01-01 | 2023-08-02
Specifications | 110d | 2023-01-01 | 2023-06-01 |  | Lior
Check Cyber aspects | 110d | 2023-01-01 | 2023-06-01 |  | Lior
Installation & Configuration | 44d | 2023-06-04 | 2023-08-02 | 80 | Lior
Observation, Operation, Management, Control (1.3) [Software] | 527d | 2021-04-01 | 2023-04-09
Operations - SOC Command & Control of ULTRASAT | 527d | 2021-04-01 | 2023-04-09
Functional design (Including incoming alerts, LSST, etc.) | 305d | 2021-04-01 | 2022-06-01 |  | Chen
Software design | 305d | 2021-04-01 | 2022-06-01 |  | Chen
GUI design | 285d | 2021-05-01 | 2022-06-01 |  | Chen
Design Review | 6d | 2022-06-02 | 2022-06-09 | 88 | Chen
Software development | 123d | 2022-06-12 | 2022-11-29 | 89 | Chen
QA & Testing | 147d | 2022-07-15 | 2023-02-05
Write testing documents | 13d | 2022-07-15 | 2022-08-01 |  | QA
Testing | 67d | 2022-08-02 | 2022-11-02 | 92 | QA
Fixes & Improvements | 134d | 2022-08-02 | 2023-02-05 | 92 | Chen
Delivery Review | 45d | 2023-02-06 | 2023-04-09 | 94 | Chen
Observation Planning | 506d | 2021-05-01 | 2023-04-06
Functional design | 285d | 2021-05-01 | 2022-06-01 |  | Eran
Software design | 196d | 2021-09-01 | 2022-06-01 |  | Chen
GUI design | 196d | 2021-09-01 | 2022-06-01 |  | Chen
Design Review | 6d | 2022-06-02 | 2022-06-09 | 100 | Chen
Algorithms development | 125d | 2022-06-12 | 2022-12-01 |  | Eran
Software development | 125d | 2022-06-12 | 2022-12-01 |  | Chen
GUI development - Desktop / Web | 59d | 2022-09-12 | 2022-12-01 |  | Chen
QA & Testing | 132d | 2022-09-14 | 2023-03-16
Write testing documents | 12d | 2022-09-14 | 2022-09-29 |  | QA
Testing | 120d | 2022-10-02 | 2023-03-16 | 106 | QA
Fixes & Improvements | 120d | 2022-10-01 | 2023-03-15 |  | Chen
Delivery Review | 16d | 2023-03-16 | 2023-04-06 | 108 | Chen
External Interfaces (1.4) - [Software] | 504d | 2022-02-01 | 2024-01-07
IAI Interface | 289d | 2022-02-01 | 2023-03-12
Complete protocol specifications with IAI-GCS | 22d | 2022-02-01 | 2022-03-02 |  | Yossi
Design Review | 6d | 2022-03-03 | 2022-03-10 | 114
Develop Incoming images handling - from IAI to Pipeline | 261d | 2022-03-13 | 2023-03-12 | 115 | Chen
Develop Metadata handling - from IAI to Pipeline and Managers | 261d | 2022-03-13 | 2023-03-12 | 115 | Chen
Develop Command & Control aspects | 261d | 2022-03-13 | 2023-03-12 | 115 | Chen
Develop Simulators and testing tools | 261d | 2022-03-13 | 2023-03-12 | 115 | Chen
QA & Testing | 54d | 2022-03-01 | 2022-05-15
Write testing documents | 9d | 2022-03-01 | 2022-03-13 |  | QA
Testing | 45d | 2022-03-14 | 2022-05-15 | 121 | QA
Fixes & Improvements | 45d | 2022-03-14 | 2022-05-15 | 121 | Chen
Delivery Review | 6d | 2023-03-13 | 2023-03-20
NASA Interface | 267d | 2022-06-01 | 2023-06-08
Communication - Infrastructure | 111d | 2022-08-01 | 2023-01-02 |  | Lior
Fiber / ADSL / Redundancy | 89d | 2022-08-01 | 2022-12-01 |  | Lior
IPSec / Cyber / Firewall | 89d | 2022-08-01 | 2022-12-01 |  | Lior
Integration & Testing | 22d | 2022-12-04 | 2023-01-02 | 128, 129 | QA
Design - requirements, protocols, access | 153d | 2022-06-01 | 2023-01-01 |  | Yossi
Design Review | 5d | 2023-01-01 | 2023-01-05
Development | 110d | 2023-01-08 | 2023-06-08 | 132 | Chen
QA & Testing | 87d | 2023-02-01 | 2023-06-01
Write testing documents | 21d | 2023-02-01 | 2023-03-01 |  | QA
Testing | 67d | 2023-03-01 | 2023-06-01 |  | QA
Fixes & Improvements | 67d | 2023-03-01 | 2023-06-01 |  | Chen
Delivery Review | 1d | 2024-01-01 | 2024-01-01
DESY Interface | 217d | 2022-06-01 | 2023-03-30
Communication - Infrastructure | 109d | 2022-08-01 | 2022-12-29 |  | Lior
Fiber / ADSL / Redundancy | 89d | 2022-08-01 | 2022-12-01 |  | Lior
IPSec / Cyber / Firewall | 89d | 2022-08-01 | 2022-12-01 |  | Lior
Integration & Testing | 21d | 2022-12-01 | 2022-12-29 |  | QA
Design - requirements, protocols, access | 153d | 2022-06-01 | 2023-01-01 |  | Yossi
Design Review | 1d | 2022-12-30 | 2022-12-30
Development | 65d | 2023-01-01 | 2023-03-30 |  | Chen
QA & Testing | 44d | 2023-01-01 | 2023-03-01 |  | QA
Write testing documents | 24d | 2023-01-01 | 2023-02-01 |  | QA
Testing | 21d | 2023-02-01 | 2023-03-01 |  | QA
Fixes & Improvements | 21d | 2023-02-01 | 2023-03-01 |  | Chen
Delivery Review | 1d | 2024-01-01 | 2024-01-01
LSST Interface | 183d | 2022-08-01 | 2023-04-12
Communication - Infrastructure | 109d | 2022-08-01 | 2022-12-29 |  | Lior
Fiber / ADSL / Redundancy | 89d | 2022-08-01 | 2022-12-01 |  | Lior
IPSec / Cyber / Firewall | 89d | 2022-08-01 | 2022-12-01 |  | Lior
Integration & Testing | 21d | 2022-12-01 | 2022-12-29 |  | QA
Design - requirements, protocols, access | 2w |  |  |  | Yossi
Design Review | 1d | 2022-12-30 | 2022-12-30
Development | 4w | 2023-01-01 | 2023-01-26 |  | Chen
QA & Testing | 31d | 2023-03-01 | 2023-04-12 |  | QA
Write testing documents | 1w | 2023-03-01 | 2023-03-07 |  | Lior
Testing | 2w | 2023-04-01 | 2023-04-12 |  | QA
Fixes & Improvements | 2w | 2023-04-01 | 2023-04-12 |  | Chen
Delivery Review | 5d | 2024-01-01 | 2024-01-07
Image & Data Processing (1.5) [Software] | 389d | 2021-01-01 | 2022-06-28
Pipeline (MATLAB) | 384d | 2021-01-01 | 2022-06-21
Functional design | 240d | 2021-01-01 | 2021-12-01 |  | Eran |  | In Progress
Databases design | 240d | 2021-01-01 | 2021-12-01 |  | Eran |  | In Progress
AstroPack Packages/Class design | 198d | 2021-03-01 | 2021-12-01 |  | Eran |  | In Progress
Software Development - Core | 198d | 2021-03-01 | 2021-12-01
Base classes (Header, Containers, etc) | 188d | 2021-03-15 | 2021-12-01 |  | Eran |  | In Progress
Base classes - Log, Database | 67d | 2021-03-01 | 2021-06-01 |  | Chen
Pipeline Manager | 67d | 2021-05-01 | 2021-08-01 |  | Chen
Single step process - From RawImage to Products | 45d | 2021-07-01 | 2021-09-01 |  | Eran
GUI | 67d | 2021-06-01 | 2021-09-01
Design & Status Review - Phase 1 | 6d | 2021-08-30 | 2021-09-06
LAST Usecase | 74d | 2021-09-01 | 2021-12-13
Specifications | 14d | 2021-09-01 | 2021-09-20 |  | Eran
Additional development - Algorithms | 30d | 2021-09-21 | 2021-11-01 | 182 | Eran
Additional development - System | 30d | 2021-09-21 | 2021-11-01 | 182 | Chen
QA & Testing | 30d | 2021-11-02 | 2021-12-13 | 184 | MatlabQA
Fixes & Improvements | 30d | 2021-11-02 | 2021-12-13 | 184 | Chen
LAST Delivery Review | 5d | 2022-01-01 | 2022-01-05
Pipeline Development
TODO HERE - DETAILS...........
QA & Testing | 100d | 2021-10-01 | 2022-02-16 |  | MatlabQA
Write testing documents | 11d | 2021-10-01 | 2021-10-14 |  | MatlabQA
Testing | 89d | 2021-10-17 | 2022-02-16 | 193 | MatlabQA
Fixes | 89d | 2021-10-17 | 2022-02-16 | 193 | Eran
Source code documentation & help | 89d | 2022-02-17 | 2022-06-21 | 195 | Eran
Pipeline Delivery Review - Phase 1 | 5d | 2022-06-22 | 2022-06-28 | 196 | Eran
Pipeline - Phase 2 - TBD | 117d | 2022-01-01 | 2022-06-12
Specifications | 24d | 2022-01-01 | 2022-02-01
Design & Status Review - Phase2 | 6d | 2022-02-02 | 2022-02-09 | 200
Development | 87d | 2022-02-10 | 2022-06-12 | 201
QA & Testing | 42d | 2022-02-02 | 2022-03-31
Write testing documents | 12d | 2022-02-02 | 2022-02-17 |  | MatlabQA
Testing | 30d | 2022-02-20 | 2022-03-31 | 204 | MatlabQA
Fixes | 30d | 2022-02-20 | 2022-03-31 | 204 | Eran
Pipeline Delivery Review - Phase 2 | 6d | 2022-04-03 | 2022-04-10 | 206 | Eran
WIS Databases & Archives | 310d | 2021-01-01 | 2022-03-09
Specifications and design | 240d | 2021-01-01 | 2021-12-01 |  | Yossi
Design Review | 6d | 2021-08-30 | 2021-09-06
Development | 111d | 2021-05-01 | 2021-09-30 |  | Chen
QA & Testing | 45d | 2022-01-01 | 2022-03-02 |  | QA
Write testing documents | 5d | 2022-01-01 | 2022-01-05 |  | QA
Testing | 4w | 2022-01-06 | 2022-02-02 | 215 | QA
Fixes & Improvements | 4w | 2022-02-03 | 2022-03-02 | 216 | Chen
Delivery Review | 5d | 2022-03-03 | 2022-03-09 | 217
Data Archiving and Accessibility (1.6) [Software] | 702d | 2021-06-01 | 2024-02-07
Databases & Archives | 139d | 2023-01-01 | 2023-07-12
Requirements and design | 44d | 2023-01-01 | 2023-03-01 |  | Yossi
Design Review | 5d | 2023-03-01 | 2023-03-07
Development - Phase 1 | 66d | 2023-04-01 | 2023-06-29 |  | Chen
Development - Phase 2 |  |  |  |  | Chen
QA & Testing | 30d | 2023-06-01 | 2023-07-12
Write testing documents | 2w | 2023-06-01 | 2023-06-14 |  | QA
Testing | 2w | 2023-06-15 | 2023-06-28 | 228 | QA
Fixes & Improvements | 2w | 2023-06-29 | 2023-07-12 | 229 | Chen
Delivery Review | 5d | 2023-07-13 | 2023-07-19 | 230
Products Access (WebApps, GUI, SQL, Python API) | 602d | 2021-06-01 | 2023-09-20
Requirements and design | 44d | 2023-01-01 | 2023-03-01 |  | Yossi
Design Review | 5d | 2023-03-02 | 2023-03-08 | 234
Development (WebApp & MobileApp) - Phase 1 | 90d | 2023-03-09 | 2023-07-12 | 235 | Chen
Additional tools design and development (Signal-to-Noise, etc.) | 44d | 2021-06-01 | 2021-08-01 |  | Chen
Development (WebApp & MobileApp) - Phase 2 | 50d | 2023-07-13 | 2023-09-20 | 236
QA & Testing | 30d | 2023-06-01 | 2023-07-12
Write testing documents | 2w | 2023-06-01 | 2023-06-14 |  | QA
Testing | 2w | 2023-06-15 | 2023-06-28 | 240 | QA
Fixed & Improvements | 2w | 2023-06-29 | 2023-07-12 | 241 | Chen
Delivery Review | 5d | 2023-07-13 | 2023-07-19 | 242
Alerts Access | 225d | 2023-01-01 | 2023-11-09
Requirements and design | 44d | 2023-01-01 | 2023-03-01 |  | Yossi
Design Review | 5d | 2023-03-01 | 2023-03-07
Development - Outgoing alerts | 66d | 2023-03-08 | 2023-06-07 | 247 | Chen
Development (WebApp & MobileApp) | 111d | 2023-06-08 | 2023-11-09 | 248 | Chen
QA & Testing | 30d | 2023-06-08 | 2023-07-19
Write testing documents and procedures | 2w | 2023-06-08 | 2023-06-21 | 248 | QA
Testing | 2w | 2023-06-22 | 2023-07-05 | 251 | QA
Fixed & Improvements | 2w | 2023-07-06 | 2023-07-19 | 252 | Chen
Delivery Review | 5d | 2024-02-01 | 2024-02-07
Partial Pipeline | 204d | 2023-01-01 | 2023-10-11
Requirements and design | 2w | 2023-01-01 | 2023-01-12 |  | Eran
Design Review | 5d | 2023-01-15 | 2023-01-19 | 257
Algorithms Development | 4w | 2023-07-01 | 2023-07-26 |  | Eran
Development | 4w | 2023-07-01 | 2023-07-26 |  | Chen
QA & Testing | 30d | 2023-09-01 | 2023-10-11
Write testing documents | 2w | 2023-09-01 | 2023-09-13 |  | QA
Testing | 2w | 2023-09-14 | 2023-09-27 | 262 | Eran
Fixed & Improvements | 2w | 2023-09-28 | 2023-10-11 | 263 | Chen
Delivery Review | 5d | 2023-10-12 | 2023-10-18 | 264
SOC System Management (1.7) [Software] | 411d | 2021-09-01 | 2023-03-29
SW & HW Infrastructure Architecture
Requirements and design |  |  |  |  | Team
SOC HMI Concept (GUI) | 351d | 2021-09-01 | 2023-01-04
Design - Functional requirements | 1w | 2021-09-01 | 2021-09-07 |  | Chen
Design - UX | 347d | 2021-09-01 | 2022-12-29 |  | Chen
Design Review | 1d | 2022-12-30 | 2022-12-30
Evaluation and improvements | 1w | 2022-12-30 | 2023-01-04 |  | Team
Cyber - Requirements and Implementation (VPN in most cases) | 20d | 2023-01-01 | 2023-01-26
IAI | 4w | 2023-01-01 | 2023-01-26 |  | Lior
DESY | 4w | 2023-01-01 | 2023-01-26 |  | Lior
NASA | 4w | 2023-01-01 | 2023-01-26 |  | Lior
LSST | 4w | 2023-01-01 | 2023-01-26 |  | Lior
Public | 4w | 2023-01-01 | 2023-01-26 |  | Lior
Procedures and Rule Engine [Development] | 65d | 2022-12-30 | 2023-03-29 |  | Chen
Requirements and design
Design Review | 1w | 2022-12-30 | 2023-01-04
Alerts | 2w | 2023-01-05 | 2023-01-18 | 288 | Chen
Target of Opportunity | 2w | 2023-01-19 | 2023-02-01 | 289 | Chen
Transients | 2w | 2023-02-02 | 2023-02-15 | 290 | Chen
Task Scheduler | 4w | 2023-02-16 | 2023-03-15 | 291 | Chen
Pending tasks | 2w | 2023-03-16 | 2023-03-29 | 292 | Chen
QA & Testing | 25d | 2023-02-12 | 2023-03-16
Write testing documents and procedures | 1w | 2023-02-12 | 2023-02-16 |  | QA
Testing | 2w | 2023-02-19 | 2023-03-02 | 295 | QA
Fixed & Improvements | 2w | 2023-03-05 | 2023-03-16 | 296 | Chen
System Monitoring | 5d | 2022-12-30 | 2023-01-04
Requirements and design
Design Review | 1w | 2022-12-30 | 2023-01-04
Development
QA & Testing
Write testing documents and procedures | 1w |  |  |  | QA
Testing | 2w |  |  |  | QA
Fixed & Improvements | 2w |  |  |  | Chen
Component Testing
QA & Testing
Write testing documents and procedures | 1w |  |  |  | QA
Testing | 2w |  |  |  | QA
Fixed & Improvements | 2w |  |  |  | Chen
QA & Integration + Acceptance Tests (1.9) | 72d | 2024-04-01 | 2024-07-09
Integration Readiness | 5d | 2024-04-01 | 2024-04-07 |  | Lior
Integration Review | 5d | 2024-04-08 | 2024-04-14 | 317 | Lior
SOC Internal - Software Component | 65d | 2024-04-01 | 2024-06-30
Integration Readiness | 1w | 2024-04-01 | 2024-04-07 |  | Lior
| 1w | 2024-04-08 | 2024-04-14 | 322 | Lior
QA & Testing | 35d | 2024-04-15 | 2024-06-02
Write testing documents | 10d | 2024-04-15 | 2024-04-28 | 323 | QA
Integration Review | 1w | 2024-04-29 | 2024-05-05 | 325
Testing | 2w | 2024-05-06 | 2024-05-19 | 326 | QA
Fixed & Improvements | 2w | 2024-05-20 | 2024-06-02 | 327 | Chen
Acceptance tests | 20d | 2024-06-03 | 2024-06-30
Tests | 1w | 2024-06-03 | 2024-06-09 | 328
Fixes | 2w | 2024-06-10 | 2024-06-23 | 330
Final tests | 1w | 2024-06-24 | 2024-06-30 | 331
SOC Internal - SOC Components Integration (HW+SW) | 65d | 2024-04-01 | 2024-06-30
Integration Readiness | 1w | 2024-04-01 | 2024-04-07 |  | Lior
| 1w | 2024-04-08 | 2024-04-14 | 335 | Lior
QA & Testing | 35d | 2024-04-15 | 2024-06-02
Write testing documents | 2w | 2024-04-15 | 2024-04-28 | 336 | QA
Integration Review | 1w | 2024-04-29 | 2024-05-05 | 338
Testing | 2w | 2024-05-06 | 2024-05-19 | 339 | QA
Fixed & Improvements | 2w | 2024-05-20 | 2024-06-02 | 340 | Chen
Acceptance tests | 20d | 2024-06-03 | 2024-06-30
Tests | 1w | 2024-06-03 | 2024-06-09 | 341 | UAT
Fixes | 2w | 2024-06-10 | 2024-06-23 | 343 | Chen
Final tests | 1w | 2024-06-24 | 2024-06-30 | 344 | UAT
SOC External - IAI | 72d | 2024-04-01 | 2024-07-09
Integration Readiness | 1w | 2024-04-01 | 2024-04-07
| 1w |  |  |  | Lior
QA & Testing | 35d | 2024-04-07 | 2024-05-23
Write integration documents | 2w | 2024-04-07 | 2024-04-18 |  | QA
Integration Review | 1w | 2024-04-21 | 2024-04-25 | 351
Testing | 2w | 2024-04-28 | 2024-05-09 | 352 | QA
Fixes and improvements | 2w | 2024-05-12 | 2024-05-23 | 353 | Chen
Acceptance tests | 33d | 2024-05-26 | 2024-07-09
Tests | 1w | 2024-05-26 | 2024-05-30 | 354 | UAT
Fixes | 23d | 2024-06-02 | 2024-07-02 | 356 | Chen
Final tests | 1w | 2024-07-03 | 2024-07-09 | 357 | UAT
SOC External - DESY | 59d | 2024-04-01 | 2024-06-20
Integration Readiness | 1w | 2024-04-01 | 2024-04-07
| 1w |  |  |  | Lior
QA & Testing | 35d | 2024-04-07 | 2024-05-23
Write integration documents | 2w | 2024-04-07 | 2024-04-18 |  | QA
Integration Review | 1w | 2024-04-21 | 2024-04-25 | 364
Testing | 2w | 2024-04-28 | 2024-05-09 | 365 | QA
Fixes and improvements | 2w | 2024-05-12 | 2024-05-23 | 366 | Chen
Acceptance tests | 20d | 2024-05-26 | 2024-06-20
Tests | 1w | 2024-05-26 | 2024-05-30 | 367 | UAT
Fixes | 2w | 2024-06-02 | 2024-06-13 | 369 | Chen
Final tests | 1w | 2024-06-16 | 2024-06-20 | 370 | UAT
SOC External - NASA | 59d | 2024-04-01 | 2024-06-20
Integration Readiness | 1w | 2024-04-01 | 2024-04-07 |  | Lior
| 1w | 2024-04-08 | 2024-04-14 | 375 | Lior
QA & Testing | 35d | 2024-04-07 | 2024-05-23
Write integration documents | 2w | 2024-04-07 | 2024-04-18 |  | QA
Integration Review | 1w | 2024-04-21 | 2024-04-25 | 378
Testing | 2w | 2024-04-28 | 2024-05-09 | 379 | QA
Fixes and improvements | 2w | 2024-05-12 | 2024-05-23 | 380 | Chen
Acceptance tests | 20d | 2024-05-26 | 2024-06-20 |  | UAT
Tests | 1w | 2024-05-26 | 2024-05-30 | 381 | QA
Fixes | 2w | 2024-06-02 | 2024-06-13 | 383 | Chen
Final tests | 1w | 2024-06-16 | 2024-06-20 | 384 | UAT
SOC External - LSST | 59d | 2024-04-01 | 2024-06-20
Integration Readiness | 1w | 2024-04-01 | 2024-04-07 |  | Lior
| 1w | 2024-04-08 | 2024-04-14 | 388 | Lior
QA & Testing | 35d | 2024-04-07 | 2024-05-23
Write integration documents | 2w | 2024-04-07 | 2024-04-18 |  | QA
Integration Review | 1w | 2024-04-21 | 2024-04-25 | 391
Testing | 2w | 2024-04-28 | 2024-05-09 | 392 | QA
Fixes and improvements | 2w | 2024-05-12 | 2024-05-23 | 393 | Chen
Acceptance tests | 20d | 2024-05-26 | 2024-06-20 |  | UAT
Tests | 1w | 2024-05-26 | 2024-05-30 | 394 | QA
Fixes | 2w | 2024-06-02 | 2024-06-13 | 396 | Chen
Final tests | 1w | 2024-06-16 | 2024-06-20 | 397 | UAT
Final Delivery Review | 14d | 2024-08-01 | 2024-08-20 |  | Lior
Training and Documentation (1.10) | 178d | 2024-01-01 | 2024-09-04
SOC Operation Simulator Development | 88d | 2024-04-01 | 2024-07-31
Requirements and design | 14d | 2024-04-01 | 2024-04-18
Write scenarios | 14d | 2024-04-21 | 2024-05-08 | 406
Software design | 14d | 2024-05-09 | 2024-05-28 | 407
Design Review | 6d | 2024-05-29 | 2024-06-05 | 408
Software development | 40d | 2024-06-06 | 2024-07-31 | 409
Evaluation
QA & Testing | 25d | 2024-08-01 | 2024-09-04
Write testing documents | 1w | 2024-08-01 | 2024-08-07 | 410 | QA
Testing | 2w | 2024-08-08 | 2024-08-21 | 413 | QA
Fixed & Improvements | 2w | 2024-08-22 | 2024-09-04 | 414 | Chen
Documentation | 90d | 2024-01-01 | 2024-05-05
Write operating procedures | 30d | 2024-01-01 | 2024-02-11
Write troubleshooting procedures | 30d | 2024-02-12 | 2024-03-24 | 418
Write maintenance procedures | 30d | 2024-03-25 | 2024-05-05 | 419
Training Materials | 30d | 2024-05-06 | 2024-06-16
Write training docuements | 30d | 2024-05-06 | 2024-06-16 | 420 | TechWriter
Help Desk (originally in 1.3.3) - Check UVDesk | 80d | 2024-01-01 | 2024-04-21
Requirements | 2w | 2024-01-01 | 2024-01-14
Research available products (Check UVDesk) | 1w | 2024-01-15 | 2024-01-21 | 427 | Chen
Functional design | 1w | 2024-01-22 | 2024-01-28 | 428
Design Review | 1w | 2024-01-29 | 2024-02-04 | 429
Write procedures | 3w | 2024-02-05 | 2024-02-25 | 430
Develop plugins if required (Optional) | 2w | 2024-02-26 | 2024-03-10 | 431 | Chen
Write training materials | 4w | 2024-03-11 | 2024-04-07 | 432
Evaluation | 2w | 2024-04-08 | 2024-04-21 | 433
Final Review
Final Delivery Review | 14d | 2024-08-01 | 2024-08-20 |  | Lior