## Pipeline Development - Detailed
Title | Description | Status | Done | Size | Priority | Request Date | Ready Date | Basic Testing Date | Advance Testing Date | Author | Advance Tester | Bugs/Features
tools
copyData | copy data (e.g., +cat, VSOP87, etc.) |  |  |  |  | 2021-04-01 |  |  |  | ?
quantileFast | fast quantile calc. using sort and index (no interp) |  | TRUE |  |  | 2021-07-01 | 2021-07-05 | 2021-07-05 |  | Eran
iqrFast | fast iqr |  | TRUE |  |  | 2021-07-01 | 2021-07-05 | 2021-07-05 |  | Eran
strNameDict2ind | look for first apperance in dictionary |  | TRUE |  |  | 2021-07-06 | 2021-07-06 | 2021-07-06 |  | Eran
LogFile | [9 empty] | Chen
write mlx with examples
AstroDB | [9 empty] | Chen
write mlx with examples
insert
query
update
createDB
Virtual Image | [9 empty] | Chen
Design
AstroTable |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
sizeCatalog |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
isemptyCatalog |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
deleteCatalog |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
isColumn |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
colname2ind |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
colind2name |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
colnameDict2ind |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
col2struct |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
isColIdentical |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
getCol |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
array2table |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
table2array |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
insertCol |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
replaceColNames |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
replaceCol |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
deleteCol |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
merge |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
sortrows |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
flipud |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
funUnary |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
min |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
max |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
query |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
queryRange |  |  | TRUE |  |  | 2021-06-15 | 2021-06-15 | 2021-06-15 |  | Eran
plotFun |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
plot |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
AstroCatalog |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
getCooTypeAuto |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
convertCooUnits |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
getCoo |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
getLonLat |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
getRADecPM |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
getXY |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
boundingCircle |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
cropXY |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
plotMapFun |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
sphere_dist |  |  | TRUE |  |  | 2021-07-07 | 2021-07-07 | 2021-07-07 |  | Eran
ImageComponent |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
FITS |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
numHDU1 | static |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
readHeader1 | static |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
read1 | static |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
read2cube | static |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
readTable1 | static |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
get_keys | static |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
mget_keys | static |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
delete_keys | static |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
write_keys | static |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
write | static |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
read2sim | static |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
numHDU |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
readHeader |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
read |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
readTable |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
ImageIO |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
read1 | static |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
write1 | static |  |  |  |  | 2021-04-01 |  |  |  | ?
readTable1 | static |  |  |  |  | 2021-04-01 |  |  |  | ?
writeTable1 | static |  |  |  |  | 2021-04-01 |  |  |  | ?
AstroHeader |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
read |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
show |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
funUnary |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
getVal |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
getStructKey |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
getCellKey |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
insertDefaultComments |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
deleteKey |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
insertKey |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
replaceVal |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
isKeyVal |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
isKeyExist |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
isImType |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
julday |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
groupByKeyVal |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
help |  |  | TRUE |  |  | 2021-06-28 | 2021-06-28 | 2021-06-28 |  | Eran
AstroImage | [5 empty] | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran |  | Add AstroWCS support
read | [5 empty] | 2021-04-01 |  |  |  | ?
write | [5 empty] | 2021-04-01 |  |  |  | ?
isemptyImage |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
sizeImage |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
astroImage2ImageComponent |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
astroImage2AstroCatalog |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
cast |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
funCat |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
funHeader |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
funHeaderScalar |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
getStructKey | [5 empty] | 2021-06-19 | 2021-06-19 | 2021-06-19 |  | Eran
funWCS
maskSet |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
isImType |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
julday |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
funUnary |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
funUnaryScalar |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
funBinaryProp |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
funBinaryImVar |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
funBinary |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
crop |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
object2array |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
plus |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
minus |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
times |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
rdivide |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
conv |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
filter |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
AstroWCS | [5 empty] | 2021-06-01 |  |  |  | Yossi
fit2wcs | [5 empty] | 2021-06-01 |  |  |  | Yossi
wcs2fit | [5 empty] | 2021-06-01 |  |  |  | Yossi
header2wcs | [5 empty] | 2021-06-01
wcs2header | [5 empty] | 2021-06-01
SIP treatment | [5 empty] | 2021-06-01 |  |  |  | Yossi
TPV treatment | [5 empty] | 2021-06-01 |  |  |  | Yossi
ZPN treatment | [5 empty] | 2021-06-01 |  |  |  | Yossi
TAN treatment | [5 empty] | 2021-06-01 |  |  |  | Yossi
SIN treatment | [5 empty] | 2021-06-01 |  |  |  | Yossi
sky2xy | [5 empty] | 2021-06-01 |  |  |  | Yossi
xy2sky | [5 empty] | 2021-06-01 |  |  |  | Yossi
AstroPSF |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran |  | Only basic exist
multiGaussianPSF | [5 empty] | 2021-04-01 |  |  |  | ?
getPSF |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
curve_of_growth |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
moment2 |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
fwhm |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
images2cube |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
funUnary | [5 empty] | 2021-04-01 |  |  |  | ?
fitPSF | [5 empty] | 2021-04-01 |  |  |  | ?
buildPSF | [5 empty] | 2021-04-01 |  |  |  | ?
Tran2D |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
design_matrix |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
nfuns |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
isParKnown |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
forward |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
backward |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
fit_simple |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
Tran2D2wcsCl |  | Need to complete |  |  |  | 2021-04-01 | 2021-05-01 |  |  | Eran
functionals2symPoly |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
functionals2polyCoef |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
symPoly |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
polyCoef |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
symPoly2deg |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
polyRep |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
imProc.stat |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
hist |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
histcounts |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
max |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
min |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
mean |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
median |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
mode |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
moment |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
quantile |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
range |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
std |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
var |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
rstd |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
imProc.background
background |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
fitSurface | fit a surface to an image, including sigma-clipping/source removal |  | TRUE |  |  | 2021-04-01 | 2021-06-21 | 2021-06-21 |  | Eran
maskSources | quick finding and masking of sources |  |  |  |  | 2021-04-01 |  |  |  | ?
imProc.dark
compare2template |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
identifyFlaringPixels |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
identifySimilarImages |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
isbias |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
isdaek |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
bias |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
debias |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
overscan |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
dark | [9 empty] | ?
dedark | [9 empty] | ?
imProc.flat |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
isFlat |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
flat |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
deflat |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
imProc.mask
maskSaturated |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
maskCR | [5 empty] | 2021-04-01 |  |  |  | ?
maskSpikes | [5 empty] | 2021-04-01 |  |  |  | ?
imProc.instCharc | [5 empty] | 2021-06-01
gainFromFlat |  |  | TRUE |  |  | 2021-06-01 | 2021-06-19 | 2021-06-19 |  | Eran
readNoiseFromBias |  |  | TRUE |  |  | 2021-06-01 | 2021-06-19 | 2021-06-19 |  | Eran
linearity |  |  | TRUE |  |  | 2021-06-01 | 2021-06-19 | 2021-06-19 |  | Eran
imProc.image
cutouts |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
images2cube |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
image2subimages |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
subimages2image | [5 empty] | 2021-04-01 |  |  |  | ?
imProc.match |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
coneSearch |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
inPolygon |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
match_caysHTM |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
match |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
mayched2matrix |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
imProc.stack
applyUnaryFun |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
divideFactor |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
subtractOffset |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
funCube |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
coadd |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
functionalResponse |  |  | TRUE |  |  | 2021-04-01 | 2021-05-01 | 2021-05-01 |  | Eran
coaddProperCore | Proper coaddition with a constant weight/PSF |  |  |  |  | 2021-04-01 |  |  |  | ?
coaddPropper | Proper coaddition with variable weight/PSF |  |  |  |  | 2021-04-01 |  |  |  | ?
imProc.cat | [5 empty] | 2021-06-01 |  |  |  | Eran
applyProperMotion |  |  | TRUE |  |  | 2021-06-01 | 2021-06-06 | 2021-06-06 |  | Eran
filterAstrometry |  |  | TRUE |  |  | 2021-06-01 | 2021-06-06 | 2021-06-06 |  | Eran
getAstrometricCatalog | [5 empty] | 2021-06-01 | 2021-06-10 |  |  | Eran
imProc.trans | [5 empty] | 2021-06-01 |  |  |  | Eran
tranAffine |  | complete testing | TRUE |  |  | 2021-06-01 | 2021-06-09 | 2021-06-15 |  | Eran
tran | [5 empty] | 2021-06-01 |  |  |  | Eran
fitTransformation |  |  | TRUE |  |  | 2021-06-01 | 2021-06-06 | 2021-06-06 |  | Eran
fitPattern |  |  | TRUE |  |  | 2021-06-01 | 2021-06-06 | 2021-06-06 |  | Eran
projection |  |  | TRUE |  |  | 2021-06-01 | 2021-06-09 | 2021-06-09 |  | Eran
projectionInv |  |  | TRUE |  |  | 2021-06-01 | 2021-06-09 | 2021-06-09 |  | Eran
imProc.psf
psf2cube | [5 empty] | 2021-06-19 | 2021-06-19 |  |  | Eran
imProc.register | [5 empty] | 2021-06-01 |  |  |  | ?
shift | [5 empty] | 2021-06-01 |  |  |  | ?
rotate | [5 empty] | 2021-06-01 |  |  |  | ?
flip
resize | [5 empty] | 2021-06-01 |  |  |  | ?
applyTran | [5 empty] | 2021-06-01 |  |  |  | ?
imProc.sources
findMeasureSources |  |  | TRUE |  |  | 2021-06-01 | 2021-06-09 | 2021-06-09 |  | Eran
findSources | [5 empty] | 2021-06-01 |  |  |  | ?
mextractor | [5 empty] | 2021-06-01 |  |  |  | ?
sextractor | [5 empty] | 2021-06-01 |  |  |  | ?
daophot | [5 empty] | 2021-06-01 |  |  |  | ?
galfit | [5 empty] | 2021-06-01 |  |  |  | ?
fitShape | [5 empty] | 2021-06-01 |  |  |  | ?
measureFocus | [5 empty] | 2021-06-18 | 2021-06-19 |  |  | Eran
calibratePhot | match source to external catalog and calibrate photomertry |  |  |  |  | 2021-06-23 |  |  |  | ?
imProc.astrometry | [5 empty] | 2021-06-01 |  |  |  | ?
astrometryCore | core astrometry for catalog |  |  |  |  | 2021-06-01 |  |  |  | ?
astrometryRefine | [5 empty] | 2021-06-01 |  |  |  | ?
astrometry | [5 empty] | 2021-06-01 |  |  |  | ?
?
imProc.subtract
properSubtractionCore | [5 empty] | 2021-06-01 |  |  |  | ?
MatchedSources |  |  | TRUE |  |  | 2021-06-11 | 2021-06-13 | 2021-06-13 |  | Eran
addMatrix |  |  | TRUE |  |  | 2021-06-11 | 2021-06-13 | 2021-06-13 |  | Eran
getMatrix |  |  | TRUE |  |  | 2021-06-11 | 2021-06-13 | 2021-06-13 |  | Eran
deleteMatrix |  |  | TRUE |  |  | 2021-06-28 | 2021-06-28 | 2021-06-28 |  | Eran
read |  |  | TRUE |  |  | 2021-06-11 | 2021-06-13 | 2021-06-13 |  | Eran
write |  |  | TRUE |  |  | 2021-06-11 | 2021-06-13 | 2021-06-13 |  | Eran
summary |  |  | TRUE |  |  | 2021-06-11 | 2021-06-13 | 2021-06-13 |  | Eran
plotRMS |  |  | TRUE |  |  | 2021-06-11 | 2021-06-13 | 2021-06-13 |  | Eran
designMatrix |  |  | TRUE |  |  | 2021-06-28 | 2021-06-28 | 2021-06-28 |  | Eran
getLC_ind |  |  | TRUE |  |  | 2021-07-06 | 2021-07-06 | 2021-07-06 |  | Eran
searchByPos | [5 empty] | 2021-07-06
plotLC | [5 empty] | 2021-07-06
ds9 | requires modifications
lcUtil
zp_sumFlux | [5 empty] | 2021-06-23 |  |  |  | ?
zp_chi2 | [5 empty] | 2021-06-23 |  |  |  | ?
sysrem | [5 empty] | 2021-06-23 |  |  |  | ?
sysremFreq | [5 empty] | 2021-06-23 |  |  |  | ?
psd | [5 empty] | 2021-06-23 |  |  |  | ?
fitMotion | [5 empty] | 2021-06-23 |  |  |  | ?
matchedFilter | [5 empty] | 2021-06-23 |  |  |  | ?
periodogram | [5 empty] | 2021-06-23 |  |  |  | ?
manuals
AstroHeader | help |  | TRUE |  |  | 2021-07-06 | 2021-07-06 | 2021-07-06 |  | Eran
AstroTable | help |  | TRUE |  |  | 2021-07-06 | 2021-07-06 | 2021-07-06 |  | Eran
Tran2D | help |  | TRUE |  |  | 2021-07-06 | 2021-07-06 | 2021-07-06 |  | Eran