## ULTRASAT MASTER Gantt
Task Name | Duration | Start | Finish | Predecessors | Assigned To | % Complete | Status | Comments
ULTRASAT MASTER GANTT
System Engineering & Infrastructure | 961d | 2021-05-01 | 2025-01-02
Architectural Design - Current Building | 35d | 2021-05-01 | 2021-06-16
Architectural Design - New Building
Hardware Procurement | 961d | 2021-05-01 | 2025-01-02 |  | Lior
Comm (Servers, Storage, Network) Room - Primary & Backup | 639d | 2021-05-01 | 2023-10-10
SOC Room | 635d | 2021-05-01 | 2023-10-04
Software Development | 638d | 2021-08-30 | 2024-02-07
Development - Operations - SOC Command & Control of ULTRASAT
Development - Observation Planning
Development - IAI Interface | 295d | 2022-02-01 | 2023-03-20
Development - DESY, NASA, LSST Interfaces | 262d | 2023-01-01 | 2024-01-01
Pipeline, Databases & Archives | 217d | 2021-08-30 | 2022-06-28
Databases & Archives | 101d | 2023-03-01 | 2023-07-19
Products Access (WebApps, GUI, SQL, Python API) | 100d | 2023-03-02 | 2023-07-19
Alerts Access | 289d | 2023-01-01 | 2024-02-07
Partial Pipeline | 5d | 2023-01-15 | 2023-01-19
SOC - Procedures and Rule Engine [Development] | 5d | 2022-12-30 | 2023-01-04 |  | Chen
SOC - System Monitoring | 5d | 2022-12-30 | 2023-01-04
SOC - QA, Testing, Integration
QA & Integration + Acceptance Tests (1.9) | 65d | 2024-04-01 | 2024-06-30
SOC Internal - Software Component | 45d | 2024-04-29 | 2024-06-30
SOC External - IAI | 5d | 2024-04-01 | 2024-04-07
SOC External - DESY, NASA, LSST | 45d | 2024-04-21 | 2024-06-20
SOC Operation Simulator Development
Documentation, Training Materials, Help-Desk
Final Delivery Review | 14d | 2024-08-01 | 2024-08-20 |  | Lior
Full Production Date | 14d | 2024-08-01 | 2024-08-20 |  | Lior