## ULTRASAT
Task Name | Duration | Start | Finish | Predecessors | Assigned To | % Complete | Status | Comments
Project Management (1.1) | 805d | 2020-12-01 | 2024-01-01 |  |  | 4%
System Engineering | 283d | 2020-12-01 | 2021-12-30 |  |  | 21%
General design (Puzzle documents) | 65d | 2020-12-01 | 2021-03-01 |  | Puzzle | 100% | Complete
Project timeline planning | 46d | 2021-05-01 | 2021-07-01 |  | Lior
In-depth design of various project requirements and components |  |  |  |  | Team
On going documentation and design of additional features | 196d | 2021-04-01 | 2021-12-30 |  | Team
Integrated Logistic Support (ILS) | 305d | 2021-04-01 | 2022-06-01
Collect information | 261d | 2021-04-01 | 2022-03-31 |  | Lior
Design | 262d | 2021-06-01 | 2022-06-01 |  | Lior
Write docuements | 262d | 2021-06-01 | 2022-06-01 |  | Lior
Standard Operating Procedure (SOP) & Training - ??? | 262d | 2021-05-01 | 2022-05-01
Collect information | 262d | 2021-05-01 | 2022-05-01 |  | Lior
Design | 262d | 2021-05-01 | 2022-05-01 |  | Lior
Write operating procedures ??? |  | 1/ |  |  | Lior
Write training materials ??? |  |  |  |  | Lior
Hardware Procurement | 698d | 2021-05-01 | 2024-01-01 |  | Lior
Comm Room | 676d | 2021-05-01 | 2023-11-30 |  | Lior
Specifications | 22d | 2023-03-01 | 2023-03-30 |  | Lior
Servers | 87d | 2023-03-01 | 2023-06-29 |  | Lior
Storage | 87d | 2023-03-01 | 2023-06-29 |  | Lior
Racks, Switches, Etc. | 87d | 2023-03-01 | 2023-06-29
Comm, Elect, A/C (Check with Hemda) | 67d | 2021-05-01 | 2021-08-01 |  | Lior
Installation and Setup | 610d | 2021-08-01 | 2023-11-30
Servers installation & configuration | 88d | 2023-08-01 | 2023-11-30
Storage installation & configuration | 88d | 2023-08-01 | 2023-11-30
Network setup | 89d | 2021-08-01 | 2021-12-01
Server, Storage, Network - Evaluation | 66d | 2023-09-01 | 2023-11-30
SOC | 132d | 2023-03-01 | 2023-08-31 |  | Lior
Specifications | 22d | 2023-03-01 | 2023-03-30
Workstations | 132d | 2023-03-01 | 2023-08-31
Monitors (Wall + Desktop) | 132d | 2023-03-01 | 2023-08-31
Office - ??? | 589d | 2021-05-01 | 2023-08-01 |  | Lior
Specifications | 1d | 2021-05-01 | 2021-05-01
Workstations | 110d | 2023-03-01 | 2023-08-01
Monitors | 110d | 2023-03-01 | 2023-08-01
New Building and Auditorium | 1d | 2024-01-01 | 2024-01-01
Specifications | 1d | 2024-01-01 | 2024-01-01
Misc | 198d | 2023-04-01 | 2024-01-01 |  | Lior
Procurement of spare parts | 1d | 2024-01-01 | 2024-01-01
Track procurement and manage installation | 1d | 2023-04-01 | 2023-04-01
Write documentation for system parts | 1d | 2023-04-01 | 2023-04-01
Infrastructure (1.2) | 940d | 2021-01-01 | 2024-08-07
SOC Room | 111d | 2021-05-01 | 2021-09-30
Passive (Cables, Connectors) | 67d | 2021-05-01 | 2021-08-01
Active (Racks, Network switches, network connection) | 45d | 2021-08-01 | 2021-09-30
Multimedia - Monitors, Matrix | 45d | 2021-08-01 | 2021-09-30
Visitor Center - New Building - TBD | 5d | 2024-08-01 | 2024-08-07
Passive (Racks, Cables, Connectors) | 1w | 2024-08-01 | 2024-08-07
Active (Network switches, network connection) | 1w | 2024-08-01 | 2024-08-07
Multimedia | 1w | 2024-08-01 | 2024-08-07
Electronics (Server) Room | 111d | 2021-05-01 | 2021-09-30
Passive (Racks, Cables, Connectors) | 67d | 2021-05-01 | 2021-08-01
Active (Network switches, network connection) | 45d | 2021-08-01 | 2021-09-30
WIS Network Requirements | 155d | 2021-05-01 | 2021-12-01
Write detailed specifications for the hardware and networking components | 46d | 2021-05-01 | 2021-07-01
Network installation and setup | 89d | 2021-08-01 | 2021-12-01
Secured Interfaces to IAI (see also Cyber) | 326d | 2021-01-01 | 2022-03-31
Communication | 66d | 2022-01-01 | 2022-03-31 |  | Lior
Fiber / ADSL / Redundancy | 44d | 2022-01-01 | 2022-03-01 |  | Lior
IPSec / Cyber / Firewall / VPN | 44d | 2022-01-01 | 2022-03-01 |  | Lior
Integration & Testing | 23d | 2022-03-01 | 2022-03-31 |  | Lior
Protocol specifications with IAI - XML etc. | 240d | 2021-01-01 | 2021-12-01 |  | Yossi
Secured WEB Interfaces (see also Cyber) | 154d | 2022-01-01 | 2022-08-02
Specifications | 110d | 2022-01-01 | 2022-06-01 |  | Lior
Check cyber aspects | 110d | 2022-01-01 | 2022-06-01 |  | Lior
Procurement | 44d | 2022-06-02 | 2022-08-02 | 71 | Lior
Observation, Operation, Management, Control (1.3) [Software] | 371d | 2021-04-01 | 2022-09-01
Operations - SOC Command & Control | 305d | 2021-04-01 | 2022-06-01
Functional design | 196d | 2021-04-01 | 2021-12-30 |  | Chen
Software design | 196d | 2021-04-01 | 2021-12-30 |  | Chen
GUI design | 176d | 2021-05-01 | 2021-12-30 |  | Chen
Software development | 109d | 2022-01-01 | 2022-05-31 |  | Chen
QA & Testing | 67d | 2022-03-01 | 2022-06-01
Testing | 67d | 2022-03-01 | 2022-06-01 |  | QA
Fixes & Improvements | 67d | 2022-03-01 | 2022-06-01 |  | Chen
Observation Planning | 351d | 2021-05-01 | 2022-09-01
Functional design | 176d | 2021-05-01 | 2021-12-30 |  | Yossi
Software design | 87d | 2021-09-01 | 2021-12-30 |  | Chen
GUI design | 66d | 2021-09-01 | 2021-12-01 |  | Chen
Software development | 66d | 2022-01-01 | 2022-03-31 |  | Eran
Software develpment | 66d | 2022-01-01 | 2022-03-31 |  | Chen
GUI development - Desktop / Web | 67d | 2022-05-01 | 2022-08-01 |  | Chen
QA & Testing | 67d | 2022-06-01 | 2022-09-01
Testing | 67d | 2022-06-01 | 2022-09-01 |  | QA
Fixes & Improvements | 67d | 2022-06-01 | 2022-09-01 |  | Chen
Component Testing | 111d | 2022-04-01 | 2022-09-01
Testing specifications | 43d | 2022-04-01 | 2022-05-30 |  | QA
Testing | 90d | 2022-05-01 | 2022-09-01 |  | QA
Fixes & Improvements | 67d | 2022-06-01 | 2022-09-01
External Interfaces (1.4) - [Software]
IAI Interface
Complete protocol specifications with IAI |  |  |  |  | Yossi
Develop Incoming images handling - from IAI to Pipeline | 2w |  |  |  | Chen
Develop Metadata handling - from IAI to Pipeline and Managers | 4w |  |  |  | Chen
Develop Command & Control aspects | 8w |  |  |  | Chen
Develop Simulators and testing tools | 4w |  |  |  | Chen
QA & Testing |  |  |  |  | QA
Testing specifications |  |  |  |  | QA
Testing |  |  |  |  | QA
Fixes & Improvements | 8w |  |  |  | Chen
NASA Interface
Communication - Infrastructure |  |  |  |  | Lior
Fiber / ADSL / Redundancy | 1w |  |  |  | Lior
IPSec / Cyber / Firewall | 1w |  |  |  | Lior
Integration & Testing | 2w |  |  |  | QA
Design - requirements, protocols, access | 2w |  |  |  | Yossi
Development | 4w |  |  |  | Chen
QA & Testing |  |  |  |  | QA
Testing |  |  |  |  | QA
Fixes & Improvements | 4w |  |  |  | Chen
DESY Interface
Communication - Infrastructure |  |  |  |  | Lior
Fiber / ADSL / Redundancy | 1w |  |  |  | Lior
IPSec / Cyber / Firewall | 1w |  |  |  | Lior
Integration & Testing | 1w |  |  |  | QA
Design - requirements, protocols, access | 2w |  |  |  | Yossi
Development | 4w |  |  |  | Chen
QA & Testing |  |  |  |  | QA
Write testing documents | 1w |  |  |  | QA
Testing | 2w |  |  |  | QA
Fixes & Improvements | 4w |  |  |  | Chen
LSST Interface
Communication - Infrastructure |  |  |  |  | Lior
Fiber / ADSL / Redundancy | 1w |  |  |  | Lior
IPSec / Cyber / Firewall | 1w |  |  |  | Lior
Integration & Testing | 1w |  |  |  | QA
Design - requirements, protocols, access | 2w |  |  |  | Yossi
Development | 4w |  |  |  | Chen
QA & Testing |  |  |  |  | QA
Write testing documents | 1w |  |  |  | Lior
Testing | 2w |  |  |  | QA
Fixes & Improvements | 2w |  |  |  | Chen
Public Interface
Communication - Infrastructure
Fiber / ADSL / Redundancy | 1w |  |  |  | Lior
IPSec / Cyber / Firewall | 1w |  |  |  | Lior
Integration & Testing | 1w |  |  |  | Lior
Design - requirements, protocols, access | 2w |  |  |  | Yossi
Development | 8w |  |  |  | Chen
QA & Testing |  |  |  |  | QA
Write testing documents | 1w |  |  |  | QA
Testing | 4w |  |  |  | QA
Fixes & Improvements | 4w |  |  |  | Chen
Image & Data Processing (1.5) [Software] |  | 2021-01-01
Pipeline (MATLAB) |  | 2021-01-01
Functional design |  | 2021-01-01 |  |  | Eran |  | In Progress
Databases design |  | 2021-01-01 |  |  | Eran |  | In Progress
wcslib Matlab wrapper |  | 2021-01-15 |  |  | Chen
Classes design |  | 2021-03-01 |  |  | Eran |  | In Progress
Base classes (Header, Containers, etc) |  | 2021-03-15 |  |  | Eran |  | In Progress
Base classes - Log, Database |  |  |  |  | Chen
Pipeline Manager |  |  |  |  | Chen
Phase 1: Single step process - From RawImage to Products |  |  |  |  | Eran
Phase 2: LAST Project - Testcase
Specifications |  |  |  |  | Eran
Additional development |  |  |  |  | Eran
Additional development |  |  |  |  | Chen
QA & Testing |  |  |  |  | Sagi
Fixes & Improvements |  |  |  |  | Chen
Pipeline GUI |  |  |  |  | Chen
Design Pipeline GUI | 1w |  |  |  | Chen
Develop Pipeline GUI | 2w |  |  |  | Chen
QA & Testing |  |  |  |  | QA
Write testing documents | 1w |  |  |  | Eran
Testing | 8w |  |  |  | QA
Fixes | 4w |  |  |  | Eran
Source code documentation & help | 2w |  |  |  | Eran
WIS Databases & Archives
Specifications and design | 1w |  |  |  | Yossi
Configurations - databases, replications, etc. | 2w |  |  |  | Chen
Development | 8w |  |  |  | Chen
QA & Testing |  |  |  |  | QA
Write testing documents | 1w |  |  |  | QA
Testing | 4w |  |  |  | QA
Fixes & Improvements | 4w |  |  |  | Chen
Data Archiving and Accessibility (1.6) [Software]
Databases & Archives
Requirements and design | 2w |  |  |  | Yossi
Development | 8w |  |  |  | Chen
QA & Testing
Write testing documents | 1w |  |  |  | QA
Testing | 4w |  |  |  | QA
Fixes & Improvements | 4w |  |  |  | Chen
Products Access
Requirements and design | 2w |  |  |  | Yossi
Development (WebApp & MobileApp) | 16w |  |  |  | Chen
Additional tools design and development (Signal-to-Noise, etc.) | 16w |  |  |  | Chen
QA & Testing
Write testing documents and procedures | 1w |  |  |  | QA
Testing | 4w |  |  |  | QA
Fixed & Improvements | 4w |  |  |  | Chen
Alerts Access
Requirements and design |  |  |  |  | Yossi
Development - Handle incoming alerts | 2w |  |  |  | Chen
Development - Outgoing alerts | 2w |  |  |  | Chen
Development (WebApp & MobileApp) | 4w |  |  |  | Chen
QA & Testing
Write testing documents and procedures | 1w |  |  |  | QA
Testing | 2w |  |  |  | QA
Fixed & Improvements | 2w |  |  |  | Chen
Partial Pipeline
Requirements and design |  |  |  |  | Eran
Development |  |  |  |  | Eran
Development |  |  |  |  | Chen
QA & Testing
Testing |  |  |  |  | QA
Fixed & Improvements |  |  |  |  | Eran
Fixed & Improvements |  |  |  |  | Chen
SOC System Management (1.7) [Software]
SW & HW Infrastructure Architecture
Requirements and design |  |  |  |  | Team
Internal & External Interfaces [Development]
IAI
DESY
NASA
Public
SOC HMI Concept (GUI)
Design - Functional requirements | 1w |  |  |  | Chen
Design - UX | 2w |  |  |  | Chen
Evaluation and improvements | 1w |  |  |  | Team
Cyber - Requirements and Implementation (VPN in most cases)
IAI | 1w |  |  |  | Lior
DESY | 1w |  |  |  | Lior
NASA | 1w |  |  |  | Lior
LSST | 1w |  |  |  | Lior
Public | 1w |  |  |  | Lior
Procedures and Rule Engine [Development]
Alerts | 1w |  |  |  | Chen
Target of Opportunity | 1w |  |  |  | Chen
Transients | 1w |  |  |  | Chen
Task Scheduler | 1w |  |  |  | Chen
Pending tasks | 1w |  |  |  | Chen
QA & Testing
Write testing documents and procedures | 1w |  |  |  | QA
Testing | 2w |  |  |  | QA
Fixed & Improvements | 2w |  |  |  | Chen
System Monitoring
QA & Testing
Write testing documents and procedures | 1w |  |  |  | QA
Testing | 2w |  |  |  | QA
Fixed & Improvements | 2w |  |  |  | Chen
Component Testing
QA & Testing
Write testing documents and procedures | 1w |  |  |  | QA
Testing | 2w |  |  |  | QA
Fixed & Improvements | 2w |  |  |  | Chen
QA & Integration + Acceptance Tests (1.9)
SOC Internal - Software Component
QA & Testing
Write testing documents and procedures | 1w |  |  |  | QA
Testing | 2w |  |  |  | QA
Fixed & Improvements | 2w |  |  |  | Chen
SOC Internal - SOC Components Integration (HW+SW)
QA & Testing
Write testing documents and procedures | 1w |  |  |  | QA
Testing | 2w |  |  |  | QA
Fixed & Improvements | 2w |  |  |  | Chen
SOC External - IAI
Write integration documents |  |  |  |  | QA
Design automation & manual testing |  |  |  |  | QA
Develop automation & simulations
Run automation |  |  |  |  | QA
Perform manual testing |  |  |  |  | QA
Fixes and improvements
Acceptance tests
SOC External - DESY
Write integration documents |  |  |  |  | QA
Design automation & manual testing |  |  |  |  | QA
Develop automation & simulations
Run automation |  |  |  |  | QA
Perform manual testing |  |  |  |  | QA
Fixes and improvements
Acceptance tests
SOC External - NASA
Write integration documents |  |  |  |  | QA
Design automation & manual testing |  |  |  |  | QA
Develop automation & simulations
Run automation |  |  |  |  | QA
Perform manual testing |  |  |  |  | QA
Fixes and improvements
Acceptance tests
SOC External - LSST
Write integration documents |  |  |  |  | QA
Design automation & manual testing |  |  |  |  | QA
Develop automation & simulations
Run automation |  |  |  |  | QA
Perform manual testing |  |  |  |  | QA
Fixes and improvements
Acceptance tests
Training and Documentation (1.10)
SOC Operation Simulator Development
Requirements and design
Write scenarios
Software design
Software development
Evaluation
QA & Testing
Write testing documents and procedures | 1w |  |  |  | QA
Testing | 2w |  |  |  | QA
Fixed & Improvements | 2w |  |  |  | Chen
Documentation
Write operating procedures
Write troubleshooting procedures
Write maintenance procedures
Training Materials
Write training docuements |  |  |  |  | TechWriter
Help Desk (originally in 1.3.3)
Requirements
Research available products (Check UVDesk) |  |  |  |  | Chen
Functional design
Write procedures
Develop plugins if required (Optional) |  |  |  |  | Chen
Write training materials
Evaluation