## ULTRASAT MASTER Gantt
Task Name | Duration | Start | Finish | Predecessors | Assigned To | % Complete | Status | Comments
ULTRASAT MASTER GANTT
Last updated: 27/06/2021
System Engineering & Infrastructure | 1046d | 2021-05-01 | 2025-05-01
Architectural Design - Current Building | 35d | 2021-05-01 | 2021-06-16
Architectural Design - New Building
Hardware Procurement | 961d | 2021-05-01 | 2025-01-02 |  | Lior
Comm (Servers, Storage, Network) Room - Primary & Backup | 639d | 2021-05-01 | 2023-10-10
SOC Room | 635d | 2021-05-01 | 2023-10-04
Visitor Center - New Building - TBD | 87d | 2025-01-01 | 2025-05-01
WIS Network Requirements | 590d | 2021-05-01 | 2023-08-02
Secured Interfaces to IAI (see also Cyber) | 7d | 2022-02-02 | 2022-02-10
Secured WEB Interfaces (DESY, NASA, LSST, Public) - see also Cyber | 154d | 2023-01-01 | 2023-08-02
Software Development | 810d | 2021-01-01 | 2024-02-07
Development - Operations - SOC Command & Control of ULTRASAT
Development - Observation Planning
Development - IAI Interface | 295d | 2022-02-01 | 2023-03-20
Development - NASA Interface | 262d | 2023-01-01 | 2024-01-01
Development - DESY Interface | 263d | 2022-12-30 | 2024-01-01
Development - LSST Interface | 267d | 2022-12-30 | 2024-01-07
Pipeline - Phase 1 | 217d | 2021-08-30 | 2022-06-28
Pipeline - Phase 2 | 48d | 2022-02-02 | 2022-04-10
WIS Databases & Archives | 310d | 2021-01-01 | 2022-03-09
Databases & Archives |  | 2023-03-01 | 2023-07-19
Products Access (WebApps, GUI, SQL, Python API) | 100d | 2023-03-02 | 2023-07-19
Alerts Access | 289d | 2023-01-01 | 2024-02-07
Partial Pipeline | 5d | 2023-01-15 | 2023-01-19
SOC - Procedures and Rule Engine [Development] | 5d | 2022-12-30 | 2023-01-04 |  | Chen
SOC - System Monitoring | 5d | 2022-12-30 | 2023-01-04
SOC - QA & Testing
SOC - Component Testing
QA & Integration + Acceptance Tests (1.9) | 102d | 2024-04-01 | 2024-08-20
SOC Internal - Software Component |  | 2024-04-29 | 2024-06-30
SOC External - IAI |  | 2024-04-01 | 2024-04-07
SOC External - DESY | 45d | 2024-04-21 | 2024-06-20
SOC External - NASA | 59d | 2024-04-01 | 2024-06-20
SOC External - LSST | 40d | 2024-04-21 | 2024-06-13
Final Delivery Review | 14d | 2024-08-01 | 2024-08-20 |  | Lior
Training and Documentation (1.10) | 147d | 2024-01-01 | 2024-07-23
SOC Operation Simulator Development | 40d | 2024-05-29 | 2024-07-23
Documentation | 90d | 2024-01-01 | 2024-05-05
Training Materials | 30d | 2024-05-06 | 2024-06-16
Help Desk | 5d | 2024-01-29 | 2024-02-04
Full Production Date | 14d | 2024-08-01 | 2024-08-20 |  | Lior